## Slide 1: Understanding the Grant Lifecycle
From Opportunity to Closeout for Federal and Non-Governmental Grants
Sandra E. Ray, CPA
Notes: INTRODUCTION (5 minutes) Good afternoon everyone. Today we're going to take a practical look at the complete grant lifecycle, beginning with identifying funding opportunities and ending with grant closeout and organizational learning. For many nonprofit organizations, grants are a critical funding source. Some come from federal agencies, some from state governments, and many come from private foundations, family foundations, community foundations, corporate giving programs, and other non-governmental sources. While the requirements may differ, successful grant management follows many of the same principles regardless of where the funding comes from.

## Slide 2: Grant Management Is More Than Winning Funding
It's about showing that your organization can:
Use funds responsibly
Produce measurable results
Document activities appropriately
Stay accountable to funders and stakeholders
Many nonprofits focus on winning grants. Funders often care more about what happens after the check arrives.
Notes: Grant management is not merely about obtaining funding. It's about demonstrating that your organization can: - Use funds responsibly - Produce measurable results - Document activities appropriately - Maintain accountability to funders and stakeholders Many nonprofits become focused on winning grants. However, funders are often more concerned with what happens after the check arrives.

## Slide 3: Three Questions to Keep in Mind Today
1
Are we spending the money appropriately?
2
Can we prove it?
3
Are we achieving the outcomes we promised?
If you can consistently answer these, you're already positioned for long-term grant success.
Notes: Throughout today's discussion, consider these three questions: Question 1: Are we spending the money appropriately? Question 2: Can we prove it? Question 3: Are we achieving the outcomes we promised? If you can consistently answer those questions, you're already positioned for long-term grant success.

## Slide 4: Today's Roadmap: Six Stages of the Grant Lifecycle
1
Find & Assess
2
Prepare & Submit
3
Accept & Set Up
4
Manage
5
Monitor & Report
6
Closeout & Learning
Then: five reminders nonprofits should keep in mind in 2026 (5 min)
Notes: We'll walk through six stages of the grant lifecycle: 1. Finding and assessing opportunities 2. Preparing and submitting applications 3. Accepting and setting up awards 4. Managing the grant 5. Monitoring and reporting 6. Closing out the grant We'll conclude by discussing several important developments nonprofits should keep in mind in 2026. There will be three polling questions along the way. Please answer each one; they count toward attendance requirements.

## Slide 5: Find and Assess the Opportunity
01
The question isn't "How quickly can we apply?" It's "Should we apply?"
Notes: STAGE 1: FIND AND ASSESS THE OPPORTUNITY (10 minutes) When organizations discover a grant opportunity, the first reaction is often excitement. Someone sees $50,000 available, $100,000 available, maybe even $500,000 available. The conversation immediately becomes: "How quickly can we apply?" A better question is: "Should we apply?"

## Slide 6: Not Every Grant Is a Good Grant
Instead of asking
"How quickly can we apply?"
ask
"Should we apply?"
Sometimes…
The funded activities don't align with your mission
Reporting requirements exceed your staffing capacity
Matching requirements create financial strain
Long-term commitments continue after funding ends
Notes: Not every grant is a good grant. Sometimes a grant provides funding for activities that don't align with your mission. Sometimes reporting requirements exceed your staffing capacity. Sometimes matching requirements create financial strain. Sometimes the grant requires long-term commitments that continue after funding ends.

## Slide 7: Ask These Questions Before You Apply
Eligibility requirements
Program objectives
Geographic restrictions
Matching requirements
Staffing requirements
Reporting expectations
Performance measures
Required partnerships
Sustainability expectations
Timeline requirements
Notes: Before applying, evaluate: - Eligibility requirements - Program objectives - Geographic restrictions - Matching requirements - Staffing requirements - Reporting expectations - Performance measures - Required partnerships - Sustainability expectations - Timeline requirements

## Slide 8: Federal vs. Non-Governmental Grants
Federal Grants
Typically include
Significant compliance requirements
Uniform Guidance (2 CFR 200) rules
Detailed financial reporting
Performance reporting
Procurement requirements
Single Audit implications
Foundation & Corporate Grants
Often focus more on
Mission alignment
Community impact
Outcomes
Storytelling
Stewardship
Relationship building
Both expect accountability. Foundations may ask for outcome and financial reports, site visits, success stories, and board engagement.
Notes: There are important differences. Federal grants typically include significant compliance requirements, Uniform Guidance considerations (Title 2 of the Code of Federal Regulations, Part 200, or 2 CFR 200), detailed financial reporting, performance reporting, procurement requirements, and Single Audit implications. Foundation and corporate grants may focus more heavily on mission alignment, community impact, outcomes, storytelling, stewardship, and relationship building. Even though private grants often have fewer compliance requirements, they still expect accountability. Many foundations may request outcome reports, financial reports, site visits, success stories, and board engagement.

## Slide 9: Example: A $75,000 Youth Programming Grant
$75,000
offered by a foundation to expand youth programming
Before saying yes, ask:
Do we have qualified staff?
Do we have facility space?
Can we sustain services after the grant ends?
Can we measure outcomes effectively?
Sometimes saying "no" to a grant is the most responsible decision.
Notes: Example discussion: Imagine a foundation offers $75,000 to expand youth programming. Ask: - Do we have qualified staff? - Do we have facility space? - Can we sustain services after the grant ends? - Can we measure outcomes effectively? Sometimes saying "no" to a grant is the most responsible decision. Practical takeaway: Successful organizations pursue opportunities that fit their strategic plan rather than changing their mission to chase funding.

## Slide 10: Polling Question #1
When evaluating a new grant opportunity, what is the MOST important consideration before deciding to apply?
A
The amount of funding available
B
Whether the grant aligns with the organization's mission and capacity
C
Whether another organization already received a similar grant
D
Whether the application deadline is more than 30 days away
Notes: POLLING QUESTION #1 (attendance check) Correct answer: B, whether the grant aligns with the organization's mission and capacity. Facilitator comment: "Many organizations are tempted to focus first on the dollar amount. However, the most successful nonprofits evaluate whether the grant aligns with their mission, staffing capacity, reporting capabilities, and long-term strategic goals before applying."

## Slide 11: Prepare and Submit the Application
02
The application is a business plan, operating plan, accountability plan and performance commitment in one.
Notes: STAGE 2: PREPARE AND SUBMIT THE APPLICATION (10 minutes) Once you've determined the opportunity fits your organization, the application process begins.

## Slide 12: What Most Grant Applications Include
01
Narrative proposal
02
Organizational description
03
Program design
04
Outcomes & evaluation plan
05
Budget
06
Budget narrative
07
Board information
08
Financial information
09
Financial statements (audited/reviewed)
10
Tax-exemption documentation
Notes: Most grant applications include: - Narrative proposal - Organizational description - Program design - Outcomes and evaluation plan - Budget - Budget narrative - Board information - Financial information - Audited financial statements - Tax exemption documentation

## Slide 13: Strong Applications Are Never Built in Isolation
Executive leadership
Program staff
Finance personnel
Development staff
Evaluation staff
Bring finance in early so the budget can actually support what the program promises.
Notes: Applications should never be developed in isolation. The strongest applications involve: - Executive leadership - Program staff - Finance personnel - Development staff - Evaluation staff

## Slide 14: Make the Budget Match the Story
THE NARRATIVE SAYS
"We will double the number of individuals served."
BUT THE BUDGET SHOWS
No additional staff
No additional supplies
No additional program costs
Funders notice. The budget and the narrative should tell the same story.
Notes: One of the most common mistakes occurs when the narrative says: "We will double the number of individuals served." But the budget shows no additional staff, no additional supplies, and no additional program costs. Funders notice. The budget and narrative should tell the same story.

## Slide 15: Questions Finance Should Ask
Can salaries be supported?
Are fringe benefits included?
What indirect costs exist?
Who will supervise the program?
What technology is needed?
What costs are not allowable?
Notes: Questions finance should ask: - Can salaries be supported? - Are fringe benefits included? - What indirect costs exist? - Who will supervise the program? - What technology is needed? - What costs are not allowable?

## Slide 16: Outputs vs. Outcomes
Outputs
What happened
500 meals served
100 tutoring sessions provided
25 workshops conducted
Outcomes
What changed
Reading scores improved
Food insecurity decreased
Employment increased
Funders increasingly want evidence of impact, not just activity.
Notes: Funders increasingly care about outcomes. Outputs tell us what happened. Examples: 500 meals served, 100 tutoring sessions provided, 25 workshops conducted. Outcomes tell us what changed. Examples: reading scores improved, food insecurity decreased, employment increased. Funders increasingly want evidence of impact. Practical takeaway: The application is not merely a request for money. It is a business plan, operating plan, accountability plan, and performance commitment all rolled into one document.

## Slide 17: Accept and Set Up the Award
03
Congratulations, you received the grant. Now what?
Notes: STAGE 3: ACCEPT AND SET UP THE AWARD (8 minutes) Congratulations. Your organization receives the grant. Now what? Many organizations celebrate the award but underestimate the importance of implementation planning.

## Slide 18: Read the Award Carefully
Never assume the approved award matches the application you submitted.
Review:
Award amount
Budget restrictions
Grant period
Reporting deadlines
Payment method
Match requirements
Special conditions
Notes: Read the award carefully. Never assume the approved award matches the submitted application. Review: - Award amount - Budget restrictions - Grant period - Reporting deadlines - Payment method - Match requirements - Special conditions

## Slide 19: Hold a Kickoff Meeting and Set Up Tracking
Internal grant kickoff meeting
Executive leadership
Program managers
Finance staff
Development staff
Compliance personnel
Everyone should know their responsibilities.
Establish financial tracking
Grant-specific accounts
Class tracking
Fund tracking
Cost centers
Budget monitoring reports
Grant activity must be clearly identifiable.
Notes: A best practice is holding a grant kickoff meeting involving executive leadership, program managers, finance staff, development staff, and compliance personnel. Everyone should know their responsibilities. Establish financial tracking. Set up grant-specific accounts, class tracking, fund tracking, cost centers, and budget monitoring reports. The organization's accounting system must allow grant activity to be clearly identified.

## Slide 20: Decide How You'll Document Everything
Where records will be stored
Who maintains records
Retention requirements
Support needed for expenditures
Good setup prevents future compliance problems.
The best time to prepare for an audit is before spending begins.
Notes: Documentation systems. Determine: - Where records will be stored - Who maintains records - Retention requirements - Support needed for expenditures Practical takeaway: Good setup prevents future compliance problems. The best time to prepare for an audit is before spending begins.

## Slide 21: Manage the Grant
04
This stage takes up most of the lifecycle. It's where services are delivered and money is spent.
Notes: STAGE 4: MANAGE THE GRANT (10 minutes) This stage occupies most of the grant lifecycle. This is where services are delivered and money is spent.

## Slide 22: Keep Three Areas Aligned
1
Approved budget
2
Actual expenditures
3
Program outcomes
When one falls out of alignment, problems often follow.
Notes: Keep three areas aligned: 1. Approved budget 2. Actual expenditures 3. Program outcomes When one falls out of alignment, problems often follow.

## Slide 23: Cost Standards: Federal and Private
Federal costs generally must be
Allowable
Allocable
Reasonable
Consistently treated
Properly documented
Private funders still expect
Responsible stewardship
Appropriate use of funds
Supporting documentation
Achievement of grant objectives
Different terminology, similar expectations.
Notes: Federal grant cost standards. Federal costs generally must be allowable, allocable, reasonable, consistently treated, and properly documented. Private grant considerations. Private funders may not use the same terminology, but expectations remain similar. They still expect responsible stewardship, appropriate use of funds, supporting documentation, and achievement of grant objectives.

## Slide 24: Personnel and Procurement
Personnel costs
Often the largest expenditure. Consider:
Time documentation
Payroll allocations
Benefit allocations
Supervisory review
Procurement & purchasing
Organizations should follow:
Written policies
Approval requirements
Conflict-of-interest safeguards
Competitive purchasing, when applicable
Notes: Personnel costs. Personnel often represent the largest expenditure. Consider time documentation, payroll allocations, benefit allocations, and supervisory review. Procurement and purchasing. Organizations should follow written policies, approval requirements, conflict-of-interest safeguards, and competitive purchasing requirements when applicable.

## Slide 25: Real-World Example: Can Funds Simply Be Shifted?
Chart: Grant budget by category
| Personnel | Supplies | Travel
Grant budget | 40000 | 10000 | 5000
Halfway through, travel isn't needed.
Can the $5,000 simply be moved to another category?
Maybe. Maybe not.
Review grant terms before any significant budget revision.
Notes: Real-world example. Suppose a grant budget includes $40,000 personnel, $10,000 supplies, and $5,000 travel. Halfway through the project, travel isn't needed. Can funds simply be shifted? Maybe. Maybe not. Always review grant terms before making significant budget revisions. Practical takeaway: The goal isn't paperwork. The goal is maintaining evidence that resources were used appropriately.

## Slide 26: Polling Question #2
Which of the following represents a key principle of effective grant management?
A
Spend all grant funds before the grant period ends
B
Keep the approved budget, actual expenditures and program outcomes aligned
C
Wait until the final report to review financial performance
D
Let program staff approve all expenditures without review
Notes: POLLING QUESTION #2 (attendance check) Correct answer: B, maintain alignment between the approved budget, actual expenditures, and program outcomes. Facilitator comment: "Strong grant management requires organizations to continuously compare what was budgeted, what was spent, and what results were achieved. Identifying variances early creates opportunities to make corrections before reporting deadlines."

## Slide 27: Monitor, Report and Adjust
05
Grant management is an ongoing process, not an annual event.
Notes: STAGE 5: MONITOR, REPORT, AND ADJUST (10 minutes) Grant management is an ongoing process. Not an annual event.

## Slide 28: Check In Monthly and Watch for Red Flags
Ask every month
Are we on budget?
Are we providing promised services?
Are outcomes being achieved?
Are reports current?
Are remaining funds sufficient?
Common red flags
Overspending
Underspending
Missed milestones
Delayed hiring
Lower-than-expected participation
Inadequate documentation
Notes: Monthly monitoring questions. Ask monthly: - Are we on budget? - Are we providing promised services? - Are outcomes being achieved? - Are reports current? - Are remaining funds sufficient? Common red flags: overspending, underspending, missed milestones, delayed hiring, program participation lower than expected, and inadequate documentation.

## Slide 29: Reporting and Funder Stewardship
Most grants require some combination of:
Financial reports
Program reports
Outcome reports
Narrative reports
Reimbursement requests
Foundations value communication. Don't wait until the final report.
Share project updates, success stories, participant testimonials, photos and event invitations. Strong stewardship can improve future funding opportunities.
Notes: Reporting. Most grants require some combination of financial reports, program reports, outcome reports, narrative reports, and reimbursement requests. Non-governmental funder stewardship. Many foundations highly value communication. Do not wait until the final report. Consider providing project updates, success stories, participant testimonials, photos, and invitations to events. Strong stewardship can improve future funding opportunities.

## Slide 30: Subrecipient Monitoring: You Remain Accountable
If your organization passes money to another organization, you remain accountable.
Responsibilities may include:
Monitoring reports
Reviewing expenditures
Assessing performance
Addressing deficiencies
Problems found early are usually manageable. Problems found during audits or final reports are much harder to fix.
Notes: Subrecipient monitoring. If your organization passes money to another organization, you remain accountable. Responsibilities may include monitoring reports, reviewing expenditures, assessing performance, and addressing deficiencies. Practical takeaway: Problems identified early are usually manageable. Problems discovered during audits or final reports are much harder to fix.

## Slide 31: Polling Question #3
True or False: A grant is considered complete as soon as the organization spends all of the grant funds.
A
True
B
False
Notes: POLLING QUESTION #3 (attendance check) Correct answer: B, False. Facilitator comment: "Spending the funds is only one step. Grants are not fully complete until required activities have been performed, final reports submitted, financial records reconciled, outstanding items resolved, and documentation retained according to funder requirements."

## Slide 32: Closeout and Learning
06
Every grant eventually ends. Closeout is more than submitting the final report.
Notes: STAGE 6: CLOSEOUT AND LEARNING (5 minutes) Eventually every grant ends. Closeout is more than submitting the final report.

## Slide 33: Close Out and Measure Success
Closeout checklist: confirm
Activities completed
Expenditures recorded
Reports submitted
Reimbursements received
Outstanding obligations resolved
Documentation retained
Measure success: ask
Did we achieve the promised outcomes?
Did we stay within budget?
Were assumptions realistic?
What challenges arose?
What would we do differently?
Notes: Closeout checklist. Confirm activities completed, expenditures recorded, reports submitted, reimbursements received, outstanding obligations resolved, and documentation retained. Measure success. Ask: Did we achieve the promised outcomes? Did we stay within budget? Were assumptions realistic? What challenges arose? What would we do differently?

## Slide 34: Turn Lessons Into Improvement
The strongest organizations use closeout findings to improve:
Future applications
Budget development
Internal controls
Program design
Outcome measurement
Every completed grant should leave you better prepared for the next one.
Notes: Turn lessons into improvement. The strongest organizations use closeout findings to improve future applications, budget development, internal controls, program design, and outcome measurement. Practical takeaway: Every completed grant should make the organization better prepared for the next one.

## Slide 35: Nonprofit Grant Reminders
2026
Five developments to keep in mind this year.
Notes: 2026 NONPROFIT GRANT REMINDERS (5 minutes)

## Slide 36: 2026 Reminders: Federal Awards
1
Uniform Guidance updates
Don't assume all federal grants work the same. Check award terms, agency guidance and program-specific requirements.
2
$1M
Single Audit threshold in federal expenditures, for fiscal years beginning on or after Oct. 1, 2024
Below the threshold? Compliance still applies.
3
Indirect cost recovery matters
Negotiated indirect cost rates
De minimis rate options
Foundation overhead allowances
Administrative cost limits
Notes: 1. Uniform Guidance updates continue to affect federal awards. Organizations should ensure staff understand which version of grant requirements applies to their awards and avoid assuming all federal grants operate identically. Always review award terms, agency guidance, and program-specific requirements. 2. Single Audit threshold. The federal threshold has increased to $1 million in federal expenditures for fiscal years beginning on or after October 1, 2024. Even organizations below the threshold must maintain compliance. 3. Indirect cost recovery matters. Many nonprofits continue to leave funding on the table by not adequately understanding indirect cost recovery opportunities. Organizations should evaluate negotiated indirect cost rates, de minimis options, foundation overhead allowances, and administrative cost limitations.

## Slide 37: 2026 Reminders: Outcomes and Diversification
4
Foundations are focused on outcomes
Private funders are asking more often:
What changed?
How do you know?
Can you demonstrate impact?
Storytelling alone is no longer enough.
5
Diversification remains critical
Avoid relying on a single source. Balance:
Individual gifts
Foundation grants
Corporate grants
Government grants
Program service revenue
Events & fundraising
Notes: 4. Foundation funders are increasingly focused on outcomes. Private funders are asking more frequently: What changed? How do you know? Can you demonstrate impact? Storytelling alone is no longer enough. Many funders want measurable evidence. 5. Diversification remains critical. Healthy nonprofits generally avoid relying on a single funding source. Consider balancing individual contributions, foundation grants, corporate grants, government grants, program service revenue, and events and fundraising activities.

## Slide 38: The Big Picture
Plan
Apply
Award
Implement
Monitor
Report
Closeout
Improve
Whatever the source of funding, the basic principles remain the same:
Know what you committed to do
Know how funds can be spent
Document your activities
Measure results
Communicate regularly
Learn from every grant
Notes: FINAL BIG PICTURE Let's step back and look at the complete grant lifecycle: Plan, Apply, Award, Implement, Monitor, Report, Closeout, Improve. Whether funding comes from the federal government, your state government, a community foundation, a family foundation, or a corporate giving program, the basic principles remain the same: - Know what you committed to do. - Know how funds can be spent. - Document your activities. - Measure results. - Communicate regularly. - Learn from every grant.

## Slide 39: Questions & Discussion
Are we spending funds appropriately? Can we prove it? Are we accomplishing what we promised?
sray@sandraraycpa.com
Notes: If your organization can consistently answer: - Are we spending funds appropriately? - Can we prove it? - Are we accomplishing what we promised? Then you're building a strong and sustainable grant management process. Thank you, and I look forward to your questions and discussion.

## Slide 40: Polling Question #4 (Bonus)
Federal and foundation grants may differ, but which expectation generally applies to both?
A
Maintaining documentation to support expenditures
B
Following Uniform Guidance
C
Completing a Single Audit
D
Obtaining federal procurement approvals
Notes: OPTIONAL BONUS POLL (use only if a fourth attendance check is needed) Correct answer: A, maintaining documentation to support expenditures. Facilitator comment: "Whether the funding comes from a federal agency, community foundation, family foundation, or corporate funder, accountability and documentation remain essential responsibilities."

## Slide 41: Thank You!
We appreciate your time and participation in today’s webinar.
Sandra E. Ray, CPA